## Forward Traceability
Requirements | Tests | Executions | Defects
FPR-8 - Attachments | FPR-117 - [Attachments] - Verify that "Select File" field is mandatory | UI sections - PASS | None
FPR-8 - Attachments - 1 defect | FPR-118 - [Attachments] - Verify that attachment cannot exceed 1 megabyte | UI sections - FAIL | FPR-141 - OPENED - "Browse" button is called "Choose file"
FPR-8 - Attachments - 2 defect | FPR-119 - [Attachments] - Verify that more than one attachment can be uploaded once | UI sections - FAIL | FPR-140 - OPENED - "Select File" allows only one file under 1Mb
FPR-141 - OPENED - "Browse" button is called "Choose file"
FPR-8 - Attachments | FPR-120 - [Attachments] - Verify that "Comment" field is optional | UI sections - PASS | None
FPR-8 - Attachments | FPR-121 - [Attachments] - Verify that "Comment" field allows 200 characters | UI sections - PASS | None
FPR-8 - Attachments | FPR-122 - [Attachments] - Verify that multiple uploads are allowed | UI sections - PASS | None
FPR-8 - Attachments | FPR-123 - [Attachments] - Verify that all files extensions are permitted | UI sections - PASS | None
FPR-8 - Attachments | FPR-124 - [Attachments] - Download uploaded file | UI sections - PASS | None
FPR-8 - Attachments | FPR-125 - [Attachments] - Verify that attachment entry can be edited | UI sections - PASS | None
FPR-8 - Attachments | FPR-126 - [Attachments] - Verify that in edit mode the user can save comment only | UI sections - PASS | None
FPR-8 - Attachments | FPR-127 - [Attachments] - Verify that in edit mode the user can cancel the actions | UI sections - PASS | None
FPR-8 - Attachments | FPR-128 - [Attachments] - Verify that the user can delete one attachment | UI sections - PASS | None
FPR-8 - Attachments | FPR-129 - [Attachments] - Verify that the user can delete multiple attachments | UI sections - PASS | None
FPR-7 - License | FPR-97 - [License] - Verify that "License Type" field is mandatory | UI sections - PASS | None
FPR-7 - License - 1 defect | FPR-98 - [License] - Verify that "License Type" field is drop-down type | UI sections - FAIL | FPR-135 - OPENED - A value is missing from "License Type" drop-down list
FPR-7 - License - 1 defect | FPR-99 - [License] - Verify that "License Number" field is mandatory | UI sections - FAIL | FPR-136 - OPENED - "License Number" field is not mandatory
FPR-7 - License | FPR-100 - [License] - Verify that "License Number" field is string type | UI sections - PASS | None
FPR-7 - License | FPR-101 - [License] - Verify that "Issued Date" field is optional | UI sections - PASS | None
FPR-7 - License | FPR-102 - [License] - Verify that "Expiry Date" field is optional | UI sections - PASS | None
FPR-7 - License - 1 defect | FPR-103 - [License] - Verify that "Issued Date" field is date type | UI sections - FAIL | FPR-137 - OPENED - User is allowed to type date in "Issued Date" field
FPR-7 - License - 1 defect | FPR-104 - [License] - Verify that "Expiry Date" field is date type | UI sections - FAIL | FPR-138 - OPENED - User is allowed to type date in "Expiry Date" field.
FPR-7 - License - 1 defect | FPR-105 - [License] - Verify that "Issued Date" field don't allow future date | UI sections - FAIL | FPR-139 - OPENED - "Issue Date" allows future date
FPR-7 - License | FPR-106 - [License] - Verify that multiple entries can be added | UI sections - PASS | None
FPR-7 - License - 3 defect | FPR-107 - [License] - Verify that License entry can be edited | UI sections - FAIL | FPR-137 - OPENED - User is allowed to type date in "Issued Date" field
FPR-138 - OPENED - User is allowed to type date in "Expiry Date" field.
FPR-139 - OPENED - "Issue Date" allows future date
FPR-7 - License | FPR-108 - [License] - Verify that a License entry can be deleted | UI sections - PASS | None
FPR-7 - License - 1 defect | FPR-144 - [License] - Verify that "Expiry Date" field cannot be set earlier than "Issued Date" field | UI sections - FAIL | FPR-147 - OPENED - "Expiry Date" field should not be earlier than "Issued Date" field
FPR-6 - Languages | FPR-81 - [Languages] - Verify that Language is a mandatory field | UI sections - PASS | None
FPR-6 - Languages | FPR-82 - [Languages] - Verify that Language field is drop-down type | UI sections - PASS | None
FPR-6 - Languages | FPR-87 - [Languages] - Verify that Fluency field is a mandatory field | UI sections - PASS | None
FPR-6 - Languages - 1 defect | FPR-88 - [Languages] - Verify that Fluency field is drop-down type | UI sections - FAIL | FPR-133 - OPENED - "Fluency" drop-down contains other values
FPR-6 - Languages | FPR-89 - [Languages] - Verify that Competency field is mandatory | UI sections - PASS | None
FPR-6 - Languages - 1 defect | FPR-90 - [Languages] - Verify that Competency field is drop-down type | UI sections - FAIL | FPR-134 - In Progress - "Competency" drop-down contains other values
FPR-6 - Languages | FPR-91 - [Languages] - Verify that Comments field is optional | UI sections - PASS | None
FPR-6 - Languages | FPR-92 - [Languages] - Verify that Comments field is string type | UI sections - PASS | None
FPR-6 - Languages | FPR-93 - [Languages] - Verify that multiple entries can be added | UI sections - PASS | None
FPR-6 - Languages | FPR-94 - [Languages] - Verify that Languages can be edited | UI sections - PASS | None
FPR-6 - Languages | FPR-95 - [Languages] - Verify that Languages can be deleted | UI sections - PASS | None
FPR-6 - Languages | FPR-96 - [Languages] - Verify that multiple language entries can be deleted | UI sections - PASS | None
FPR-5 - Skills section | FPR-71 - [Skills] - Verify that Skill field is a mandatory field. | UI sections - PASS | None
FPR-5 - Skills section - 1 defect | FPR-72 - [Skills] - Verify that Skill field is drop-down type | UI sections - FAIL | FPR-130 - OPENED - "Skill" drop-down list doesn't match with documented values
FPR-5 - Skills section - 1 defect | FPR-73 - [Skills] - Verify that Years of Experience field is string type | UI sections - FAIL | FPR-131 - OPENED - Field "Years of Experience" not allows all type of characters
FPR-5 - Skills section | FPR-74 - [Skills] - Verify that Years of Experience field is optional | UI sections - PASS | None
FPR-5 - Skills section - 1 defect | FPR-75 - [Skills] - Verify that Comments field is string type | UI sections - FAIL | FPR-132 - OPENED - "Comments" field allows only 100 characters
FPR-5 - Skills section | FPR-76 - [Skills] - Verify that Comments field is optional | UI sections - PASS | None
FPR-5 - Skills section | FPR-77 - [Skills] - Verify that multiple entries can be added | UI sections - PASS | None
FPR-5 - Skills section - 2 defect | FPR-78 - [Skills] - Verify that Skills can be edited | UI sections - FAIL | FPR-131 - OPENED - Field "Years of Experience" not allows all type of characters
FPR-132 - OPENED - "Comments" field allows only 100 characters
FPR-5 - Skills section | FPR-79 - [Skills] - Verify that Skills can be deleted | UI sections - PASS | None
FPR-5 - Skills section | FPR-80 - [Skills] - Verify that multiple skills entries can be deleted | UI sections - PASS | None
FPR-4 - Education section | FPR-57 - [Education] - Verify that Level field is a mandatory field. | UI sections - PASS | None
FPR-4 - Education section - 1 defect | FPR-58 - [Education] - Verify that Level field is drop-down type | UI sections - FAIL | FPR-110 - OPENED - "Level" drop-down contains more values
FPR-4 - Education section | FPR-59 - [Education] - Verify that Institute field is string type | UI sections - PASS | None
FPR-4 - Education section | FPR-60 - [Education] - Verify that Major/Specialization field is string type | UI sections - PASS | None
FPR-4 - Education section - 1 defect | FPR-61 - [Education] - Verify that GPA/Score field is string type | UI sections - FAIL | FPR-112 - OPENED - "GPA/Score" field allows only 25 characters
FPR-4 - Education section - 1 defect | FPR-62 - [Education] - Verify that Start Date field is date type | UI sections - FAIL | FPR-113 - OPENED - User is allowed to type date in "Start Date" field
FPR-4 - Education section - 1 defect | FPR-63 - [Education] - Verify that End Date field is date type | UI sections - FAIL | FPR-114 - OPENED - User is allowed to type date in "End Date" field
FPR-4 - Education section - 2 defect | FPR-64 - [Education] - Verify that Start Date and End Date fields don't allow future dates | UI sections - FAIL | FPR-115 - OPENED - "Start Date" allows future date
FPR-116 - OPENED - "End Date" allows future date
FPR-4 - Education section | FPR-65 - [Education] - Verify that Institute, Major/Specialization and GPA/Score fields are optional | UI sections - PASS | None
FPR-4 - Education section | FPR-66 - [Education] - Verify that Start Date and End Date fields are optional | UI sections - PASS | None
FPR-4 - Education section | FPR-67 - [Education] - Verify that multiple entries can be added | UI sections - PASS | None
FPR-4 - Education section - 3 defect | FPR-68 - [Education] - Verify that education can be edited | UI sections - FAIL | FPR-112 - OPENED - "GPA/Score" field allows only 25 characters
FPR-113 - OPENED - User is allowed to type date in "Start Date" field
FPR-114 - OPENED - User is allowed to type date in "End Date" field
FPR-4 - Education section | FPR-69 - [Education] - Verify that education entry can be deleted | UI sections - PASS | None
FPR-4 - Education section | FPR-70 - [Education] - Verify that multiple education entries can be deleted | UI sections - PASS | None
FPR-4 - Education section - 1 defect | FPR-143 - [Education] - Verify that "End Date" field cannot be set earlier than "Start Date" field | UI sections - FAIL | FPR-146 - OPENED - "End date" field should not be earlier than "Start Date" field
FPR-4 - Education section | FPR-150 - [GET] - Education when no entries are registered | API education testing - PASS | None
FPR-4 - Education section | FPR-151 - [POST] - ADD employee education | API education testing - PASS | None
FPR-4 - Education section | FPR-152 - [GET] - Education when at least one entry registered | API education testing - PASS | None
FPR-4 - Education section - 1 defect | FPR-153 - [POST] - ADD employee education when employee id not found | API education testing - FAIL | FPR-52 - In Progress - 20x HTTP response returned instead of 404
FPR-4 - Education section | FPR-154 - [POST] - ADD employee education when level education is a string | API education testing - PASS | None
FPR-4 - Education section | FPR-155 - [POST] - ADD employee education when level education missing | API education testing - PASS | None
FPR-4 - Education section | FPR-156 - [DELETE] - Employee education | API education testing - PASS | None
FPR-4 - Education section - 2 defect | FPR-157 - [DELETE] - Employee education when user not found | API education testing - FAIL | FPR-148 - OPENED - Returned message is different than expected one
FPR-54 - In Progress - 400 HTTP response instead of 404
FPR-4 - Education section - 2 defect | FPR-158 - [DELETE] - Employee education when record not found | API education testing - FAIL | FPR-148 - OPENED - Returned message is different than expected one
FPR-54 - In Progress - 400 HTTP response instead of 404
FPR-2 - Work experience section | FPR-31 - [GET] - Work experience when no entries are registered | API work experience testing - PASS | None
FPR-2 - Work experience section - 1 defect | FPR-32 - [GET] - Work experience when at least one entry registered | API work experience testing - FAIL | FPR-51 - OPENED - GET response is different than expected
FPR-2 - Work experience section | FPR-33 - [POST] - Add work experience | API work experience testing - PASS | None
FPR-2 - Work experience section - 1 defect | FPR-34 - [POST] - Add work experience when employee id is wrong | API work experience testing - FAIL | FPR-52 - In Progress - 20x HTTP response returned instead of 404
FPR-2 - Work experience section - 1 defect | FPR-35 - [POST] - Add work experience when mandatory fields are missing | API work experience testing - FAIL | FPR-52 - In Progress - 20x HTTP response returned instead of 404
FPR-2 - Work experience section - 2 defect | FPR-41 - [Work experience] - Verify that "From" and "To" fields don't allows future date | Ad hoc - FAIL | FPR-42 - OPENED - "From" field allows future date
FPR-43 - OPENED - "To" field allows future date
FPR-2 - Work experience section | FPR-44 - [PUT] - EDIT employee work experience | API work experience testing - PASS | None
FPR-2 - Work experience section - 1 defect | FPR-45 - [PUT] - EDIT employee work experience when user Id not existing | API work experience testing - FAIL | FPR-53 - OPENED - No error returned when mandatory field is wrong
FPR-2 - Work experience section - 1 defect | FPR-46 - [PUT] - EDIT employee work experience when record not found | API work experience testing - FAIL | FPR-54 - In Progress - 400 HTTP response instead of 404
FPR-2 - Work experience section | FPR-47 - [DELETE] - DELETE employee work experience | API work experience testing - PASS | None
FPR-2 - Work experience section - 1 defect | FPR-55 - [DELETE] - DELETE employee work experience when user not found | API work experience testing - FAIL | FPR-54 - In Progress - 400 HTTP response instead of 404
FPR-2 - Work experience section - 1 defect | FPR-56 - [DELETE] - DELETE employee work experience when record not found | API work experience testing - FAIL | FPR-54 - In Progress - 400 HTTP response instead of 404
FPR-2 - Work experience section - 1 defect | FPR-142 - [Work experience] - Verify that "To" field cannot be set earlier than "From" field | UI sections - FAIL | FPR-145 - OPENED - "To" field should not be earlier than "From" field